## Jira Export
Issue Key | Summary | Issue Type | Status | Priority | Assignee | Reporter | Created | Updated | Resolved | Due Date | Sprint | Epic Link | Labels | Story Points | Component/s | Fix Version/s | Time Spent | Original Estimate
SPARK-1 | Implement OAuth2 login flow with Google provider | Task | In Progress | High | Bob Martinez | PM - Sarah Wilson | 2025-09-27 | 2025-10-15 |  | 2025-10-11 | Sprint 2025-Q4-1 | User Authentication & SSO | security | 1 | Web App | v3.0.0-beta | 1.3 | 2.9
SPARK-2 | Add SAML SSO integration for enterprise customers | Bug | In Progress | High | Frank Johnson | Bob Martinez | 2025-10-11 | 2025-10-23 |  | 2025-10-30 | Sprint 2025-Q4-2 | User Authentication & SSO | analytics, backend | 8 | CI/CD | v3.0.0-beta | 5.9 | 18.5
SPARK-3 | Migrate batch ETL jobs to streaming architecture | Story | To Do | Medium | Eva Petrov | Bob Martinez | 2026-01-17 | 2026-01-20 |  | 2026-02-05 | Sprint 2026-Q1-2 | Data Pipeline Modernization | api, tech-debt | 13 | Mobile Android | v2.2.0
SPARK-4 | Build password reset flow with email verification | Bug | Done | High | Hassan Ali | Grace Liu | 2026-01-18 | 2026-02-05 | 2026-02-05 | 2026-02-03 | Sprint 2026-Q1-2 | User Authentication & SSO | auth | 1 | Web App |  | 2.7 | 3.6
SPARK-5 | Implement Apache Kafka event ingestion pipeline | Bug | In Review | Low | Hassan Ali | Carol Okonkwo | 2025-10-14 | 2025-10-18 |  | 2025-11-02 | Sprint 2025-Q4-2 | Data Pipeline Modernization | mobile, documentation | 8 | Shared Libs |  |  | 23
SPARK-6 | Build real-time dashboard widget framework | Story | Done | Low | Carol Okonkwo | Carol Okonkwo | 2026-01-20 | 2026-01-23 | 2026-01-23 | 2026-02-05 | Sprint 2026-Q1-2 | Dashboard & Reporting Engine | testing, auth | 8 | Web App |  | 27.7 | 19.7
SPARK-7 | Build data quality validation framework | Story | In Review | Medium | Eva Petrov | PM - Sarah Wilson | 2025-10-26 | 2025-11-11 |  |  | Sprint 2025-Q4-3 | Data Pipeline Modernization | auth, accessibility | 13 | Data Service | v2.1.0
SPARK-8 | Create multi-factor authentication (MFA) setup page | Story | To Do | Low | Eva Petrov | David Kim | 2026-01-14 | 2026-01-21 |  |  | Sprint 2026-Q1-2 | User Authentication & SSO | mobile | 1 | CI/CD
SPARK-9 | Implement drag-and-drop dashboard layout editor | Bug | Blocked | High | Grace Liu | David Kim | 2025-10-18 | 2025-10-24 |  |  | Sprint 2025-Q4-2 | Dashboard & Reporting Engine | accessibility, tech-debt, infra | 5 | CI/CD | v2.1.0 |  | 10.4
SPARK-10 | Create chart component library (bar, line, pie, area) | Story | Done | High | Alice Chen | Frank Johnson | 2025-09-27 | 2025-10-05 | 2025-10-05 | 2025-10-18 | Sprint 2025-Q4-1 | Dashboard & Reporting Engine | api, mobile, documentation | 2 | CI/CD | v3.0.0-beta | 8.9 | 10.5
SPARK-11 | Implement JWT token refresh mechanism | Story | In Review | Low | Alice Chen | Bob Martinez | 2025-12-31 | 2026-01-12 |  |  | Sprint 2026-Q1-1 | User Authentication & SSO | security | 1 | Data Service | v2.1.0 |  | 3.1
SPARK-12 | Add CSV/PDF export for all report views | Story | Done | Medium | Alice Chen | PM - Sarah Wilson | 2025-09-26 | 2025-10-04 | 2025-10-04 | 2025-10-18 | Sprint 2025-Q4-1 | Dashboard & Reporting Engine | auth | 5 | Shared Libs |  | 9.3 | 13.3
SPARK-13 | Redesign home screen with personalized feed | Sub-task | Done | Medium | Hassan Ali | Carol Okonkwo | 2025-10-27 | 2025-11-03 | 2025-11-03 |  | Sprint 2025-Q4-3 | Mobile App v2 Redesign | testing, backend, mobile | 2 | Mobile Android | v3.0.0-beta | 11.1 | 8
SPARK-14 | Build scheduled report email delivery system | Spike | To Do | High | Bob Martinez | David Kim | 2025-10-02 | 2025-10-05 |  |  | Sprint 2025-Q4-1 | Dashboard & Reporting Engine | documentation | 8 | Web App |  |  | 34.7
SPARK-15 | Create schema registry for event contracts | Story | Done | High | Grace Liu | Carol Okonkwo | 2025-10-28 | 2025-11-08 | 2025-11-08 |  | Sprint 2025-Q4-3 | Data Pipeline Modernization | infra | 1 | API Gateway | v2.1.0 | 3.2 | 4
SPARK-16 | Add dead letter queue handling for failed events | Sub-task | In Review | High | Eva Petrov | PM - James Taylor | 2025-10-04 | 2025-10-04 |  | 2025-10-19 | Sprint 2025-Q4-1 | Data Pipeline Modernization | frontend, api, performance | 1 | API Gateway
SPARK-17 | Implement custom date range picker for analytics | Story | In Progress | Medium | Eva Petrov | PM - Sarah Wilson | 2025-10-31 | 2025-11-08 |  |  | Sprint 2025-Q4-3 | Dashboard & Reporting Engine | accessibility | 1 | Shared Libs |  | 0.7 | 2.2
SPARK-18 | Create KPI card component with trend indicators | Story | In Review | Low | Alice Chen | Bob Martinez | 2025-10-25 | 2025-11-16 |  |  | Sprint 2025-Q4-3 | Dashboard & Reporting Engine | auth | 8 | Mobile Android | v2.1.0 |  | 17.3
SPARK-19 | Implement data partitioning strategy for time-series data | Sub-task | In Progress | High | Bob Martinez | Frank Johnson | 2025-10-04 | 2025-10-17 |  |  | Sprint 2025-Q4-1 | Data Pipeline Modernization | database | 2 | Data Service |  | 6.2 | 11.8
SPARK-20 | Implement bottom navigation with gesture support | Story | Done | Low | Grace Liu | David Kim | 2025-09-30 | 2025-10-04 | 2025-10-04 | 2025-10-11 | Sprint 2025-Q4-1 | Mobile App v2 Redesign | security | 5 | CI/CD | v2.1.0 | 17.8 | 14.5
SPARK-21 | Build offline-first data sync engine | Story | To Do | Low | Frank Johnson | PM - Sarah Wilson | 2025-10-30 | 2025-11-16 |  | 2025-11-08 | Sprint 2025-Q4-3 | Mobile App v2 Redesign | api, documentation | 1 | Mobile iOS | v3.0.0-beta |  | 5.1
SPARK-22 | Create push notification preference center | Epic | To Do | Low | David Kim | Eva Petrov | 2026-01-14 | 2026-02-05 |  | 2026-02-06 | Sprint 2026-Q1-2 | Mobile App v2 Redesign | mobile, database, auth | 2 | Data Service | v2.0.0
SPARK-23 | Build monitoring dashboard for pipeline health | Story | Done | Low | Eva Petrov | PM - Sarah Wilson | 2026-01-18 | 2026-02-01 | 2026-02-01 | 2026-02-02 | Sprint 2026-Q1-2 | Data Pipeline Modernization | security | 8 | Shared Libs |  | 36.5 | 28.1
SPARK-24 | Add drill-down navigation from summary to detail views | Bug | In Review | Low | Eva Petrov | Eva Petrov | 2026-01-17 | 2026-01-30 |  |  | Sprint 2026-Q1-2 | Dashboard & Reporting Engine | tech-debt, infra, auth | 8 | CI/CD
SPARK-25 | Build saved filters and bookmarked views | Story | Done | Medium | Bob Martinez | David Kim | 2025-09-30 | 2025-10-07 | 2025-10-07 | 2025-10-11 | Sprint 2025-Q4-1 | Dashboard & Reporting Engine | documentation, auth | 2 | API Gateway | v2.1.0 | 9.8 | 9.7
SPARK-26 | Add biometric authentication (Face ID / fingerprint) | Story | Done | Low | Bob Martinez | Grace Liu | 2025-10-13 | 2025-10-30 | 2025-10-30 | 2025-11-02 | Sprint 2025-Q4-2 | Mobile App v2 Redesign | infra | 2 | Auth Service |  | 13.9 | 9.3
SPARK-27 | Create data lineage tracking system | Bug | Done | Medium | Hassan Ali | Carol Okonkwo | 2026-01-07 | 2026-01-16 | 2026-01-16 |  | Sprint 2026-Q1-1 | Data Pipeline Modernization | analytics, database | 13 | CI/CD |  | 30.7 | 40.3
SPARK-28 | Add automated data reconciliation checks | Story | In Progress | Medium | Carol Okonkwo | Carol Okonkwo | 2025-10-13 | 2025-10-25 |  | 2025-10-28 | Sprint 2025-Q4-2 | Data Pipeline Modernization | ux, tech-debt | 1 | CI/CD | v2.1.0 | 1.9 | 5.3
SPARK-29 | Add role-based access control (RBAC) middleware | Story | To Do | Medium | Grace Liu | Grace Liu | 2026-01-22 | 2026-02-08 |  |  | Sprint 2026-Q1-2 | User Authentication & SSO | security, performance | 2 | Shared Libs | v3.0.0-beta |  | 9.4
SPARK-30 | Implement dark mode with system preference detection | Task | Done | Lowest | Alice Chen | Grace Liu | 2025-10-10 | 2025-10-31 | 2025-10-31 | 2025-11-01 | Sprint 2025-Q4-2 | Mobile App v2 Redesign | performance | 2 | Shared Libs | v3.0.0-beta | 8.7 | 6.6
SPARK-31 | Build image optimization and lazy loading | Task | Done | Medium | Bob Martinez | Hassan Ali | 2025-10-24 | 2025-11-11 | 2025-11-11 | 2025-11-13 | Sprint 2025-Q4-3 | Mobile App v2 Redesign | frontend, analytics, accessibility | 2 | Web App |  | 10 | 11.6
SPARK-32 | Build user profile settings page | Story | To Do | Medium | David Kim | Hassan Ali | 2026-01-18 | 2026-01-29 |  | 2026-01-30 | Sprint 2026-Q1-2 | User Authentication & SSO | frontend, documentation | 2 | Web App
SPARK-33 | Create onboarding flow for new users | Spike | In Progress | Medium | David Kim | Bob Martinez | 2026-01-04 | 2026-01-25 |  | 2026-01-16 | Sprint 2026-Q1-1 | Mobile App v2 Redesign | tech-debt | 8 | Shared Libs |  | 8.4 | 18.2
SPARK-34 | Add session management and device tracking | Task | To Do | Lowest | Hassan Ali | Carol Okonkwo | 2026-01-06 | 2026-01-11 |  |  | Sprint 2026-Q1-1 | User Authentication & SSO | analytics, testing, database | 3 | CI/CD | v2.2.0 |  | 8.9
SPARK-35 | Implement account lockout after failed attempts | Sub-task | In Progress | Medium | Grace Liu | Frank Johnson | 2025-10-24 | 2025-11-08 |  |  | Sprint 2025-Q4-3 | User Authentication & SSO | security, tech-debt | 0 | Mobile iOS | v2.2.0
SPARK-36 | Implement dashboard sharing with permission controls | Story | In Review | Medium | David Kim | Hassan Ali | 2025-10-03 | 2025-10-17 |  |  | Sprint 2025-Q4-1 | Dashboard & Reporting Engine | security, ux | 1 | Data Service | v2.2.0 |  | 4.1
SPARK-37 | Add pull-to-refresh with skeleton loading states | Story | Done | Medium | Eva Petrov | David Kim | 2026-01-15 | 2026-01-22 | 2026-01-22 | 2026-02-06 | Sprint 2026-Q1-2 | Mobile App v2 Redesign | security | 13 | Data Service |  | 47.3 | 40.4
SPARK-38 | Implement incremental data sync for large datasets | Task | In Progress | Medium | Eva Petrov | Alice Chen | 2025-10-04 | 2025-10-08 |  | 2025-10-11 | Sprint 2025-Q4-1 | Data Pipeline Modernization | api, accessibility, analytics | 3 | CI/CD | v2.0.0 | 5 | 12.9
SPARK-39 | Implement deep linking for shared content | Story | To Do | Low | Hassan Ali | Bob Martinez | 2025-10-25 | 2025-11-06 |  | 2025-11-08 | Sprint 2025-Q4-3 | Mobile App v2 Redesign | analytics | 2 | Mobile iOS | v2.1.0 |  | 10.1
SPARK-40 | Create embeddable widget for external sites | Story | Done | Medium | Grace Liu | Eva Petrov | 2026-01-14 | 2026-01-18 | 2026-01-18 |  | Sprint 2026-Q1-2 | Dashboard & Reporting Engine | security, performance, accessibility | 2 | API Gateway | v2.1.0 | 6.9 | 8.4
SPARK-41 | Build accessibility audit and WCAG compliance fixes | Bug | Done | Highest | Eva Petrov | Eva Petrov | 2026-01-07 | 2026-01-15 | 2026-01-15 |  | Sprint 2026-Q1-1 | Mobile App v2 Redesign | accessibility, analytics, security | 13 | Shared Libs | v2.1.0 | 85.1 | 59.7
SPARK-42 | Add data caching layer for dashboard performance | Story | Done | Medium | Eva Petrov | Hassan Ali | 2025-09-27 | 2025-10-07 | 2025-10-07 | 2025-10-15 | Sprint 2025-Q4-1 | Dashboard & Reporting Engine | infra, database, frontend | 8 | Web App |  | 46.7 | 39.5
SPARK-43 | Add social login support (GitHub, Microsoft) | Story | Done | Low | Alice Chen | Eva Petrov | 2025-09-26 | 2025-10-02 | 2025-10-02 | 2025-10-18 | Sprint 2025-Q4-1 | User Authentication & SSO | documentation | 3 | Shared Libs |  | 9.2 | 11.9
SPARK-44 | Build CDC (Change Data Capture) connector for PostgreSQL | Story | Done | Low | Frank Johnson | Grace Liu | 2026-01-07 | 2026-01-20 | 2026-01-20 |  | Sprint 2026-Q1-1 | Data Pipeline Modernization | infra | 8 | API Gateway | v2.2.0 | 26 | 19.7
SPARK-45 | Create API key management for service accounts | Story | To Do | Medium | Hassan Ali | Hassan Ali | 2026-01-14 | 2026-01-20 |  | 2026-01-31 | Sprint 2026-Q1-2 | User Authentication & SSO | database, mobile | 3 | CI/CD | v2.1.0
SPARK-46 | Create data catalog with search and discovery | Story | In Review | High | Bob Martinez | Hassan Ali | 2026-01-15 | 2026-02-04 |  |  | Sprint 2026-Q1-2 | Data Pipeline Modernization | performance, testing, mobile | 5 | Mobile iOS | v3.0.0-beta
SPARK-47 | Fix: Chart tooltip overlap on mobile viewport | Bug | In Review | Low | Carol Okonkwo | Bob Martinez | 2026-01-04 | 2026-01-17 |  | 2026-01-23 | Sprint 2026-Q1-1 | Dashboard & Reporting Engine | performance | 3 | Mobile iOS
SPARK-48 | Create app performance monitoring integration | Story | Done | Medium | Grace Liu | Hassan Ali | 2025-10-15 | 2025-10-23 | 2025-10-23 | 2025-10-28 | Sprint 2025-Q4-2 | Mobile App v2 Redesign | tech-debt | 5 | CI/CD |  | 26.5 | 26.2
SPARK-49 | Fix: Export PDF cuts off wide tables | Spike | To Do | Lowest | Frank Johnson | Bob Martinez | 2026-01-07 | 2026-01-10 |  | 2026-01-22 | Sprint 2026-Q1-1 | Dashboard & Reporting Engine | api, ux, accessibility | 1 | Auth Service | v2.2.0 |  | 4.8
SPARK-50 | Build audit log for authentication events | Sub-task | Done | Medium | Frank Johnson | Hassan Ali | 2025-11-01 | 2025-11-11 | 2025-11-11 | 2025-11-12 | Sprint 2025-Q4-3 | User Authentication & SSO | frontend, ux, database | 0 | API Gateway | v2.2.0
SPARK-51 | Fix: SSO redirect loop on expired sessions | Story | In Review | High | Grace Liu | PM - James Taylor | 2025-10-26 | 2025-10-31 |  | 2025-11-14 | Sprint 2025-Q4-3 | User Authentication & SSO | security, infra, documentation | 8 | Auth Service | v2.2.0 |  | 37.3
SPARK-52 | Fix: App crash on low-memory Android devices | Bug | In Progress | Medium | Frank Johnson | PM - James Taylor | 2025-10-28 | 2025-11-17 |  |  | Sprint 2025-Q4-3 | Mobile App v2 Redesign | infra, auth | 13 | Mobile iOS | v3.0.0-beta | 17.1 | 70.4
SPARK-53 | Fix: Push notifications not received when app is backgrounded | Story | In Progress | Medium | Alice Chen | Grace Liu | 2026-01-18 | 2026-01-18 |  | 2026-01-29 | Sprint 2026-Q1-2 | Mobile App v2 Redesign | infra, auth, performance | 8 | Data Service |  | 12.4 | 27.3
SPARK-54 | Fix: Kafka consumer lag causing data delays | Bug | Done | Medium | Eva Petrov | Hassan Ali | 2025-10-10 | 2025-10-22 | 2025-10-22 |  | Sprint 2025-Q4-2 | Data Pipeline Modernization | tech-debt, mobile | 1 | Shared Libs | v2.1.0 | 7.2 | 5.1
SPARK-55 | Fix: Schema evolution breaking downstream consumers | Bug | In Progress | High | Hassan Ali | Eva Petrov | 2026-01-19 | 2026-01-22 |  | 2026-01-30 | Sprint 2026-Q1-2 | Data Pipeline Modernization | auth | 2 | Shared Libs |  | 3.6 | 10.4
SPARK-56 | Fix: Image upload fails on slow network connections | Story | To Do | Medium | Eva Petrov | PM - James Taylor | 2025-10-02 | 2025-10-13 |  | 2025-10-14 | Sprint 2025-Q4-1 | Mobile App v2 Redesign | documentation | 5 | Mobile Android |  |  | 11.3
SPARK-57 | Spike: Evaluate React Native vs Flutter migration | Bug | To Do | Highest | Alice Chen | Eva Petrov | 2025-10-31 | 2025-11-03 |  | 2025-11-16 | Sprint 2025-Q4-3 | Mobile App v2 Redesign | infra, tech-debt | 2 | Shared Libs | v2.1.0
SPARK-58 | Fix: MFA code validation timing issue | Bug | Blocked | Medium | Frank Johnson | David Kim | 2026-01-07 | 2026-01-21 |  |  | Sprint 2026-Q1-1 | User Authentication & SSO | accessibility | 3 | Mobile Android | v2.2.0 |  | 9.3
SPARK-59 | [Mobile] Additional work item #59 | Bug | Done | Medium | Alice Chen | Alice Chen | 2025-10-01 | 2025-10-06 | 2025-10-06 |  | Sprint 2025-Q4-1 | Mobile App v2 Redesign | auth | 2 | Data Service | v2.1.0 | 5.4 | 6.6
SPARK-60 | Spike: Evaluate passkey/WebAuthn support | Sub-task | To Do | High | Eva Petrov | Carol Okonkwo | 2025-10-25 | 2025-11-15 |  |  | Sprint 2025-Q4-3 | User Authentication & SSO | tech-debt | 0 | Data Service | v2.0.0
SPARK-61 | [Mobile] Additional work item #61 | Story | To Do | Medium | Frank Johnson | PM - Sarah Wilson | 2026-01-15 | 2026-01-29 |  | 2026-01-29 | Sprint 2026-Q1-2 | Mobile App v2 Redesign | testing, performance, infra | 13 | Web App | v3.0.0-beta
SPARK-62 | [Mobile] Additional work item #62 | Story | Done | High | Bob Martinez | Frank Johnson | 2025-09-28 | 2025-10-03 | 2025-10-03 | 2025-10-19 | Sprint 2025-Q4-1 | Mobile App v2 Redesign | ux, documentation | 13 | Mobile iOS | v3.0.0-beta | 39.3 | 31.2
SPARK-63 | Fix: Dashboard loading spinner stuck on slow connections | Story | In Progress | Medium | Hassan Ali | Grace Liu | 2026-01-06 | 2026-01-09 |  | 2026-01-20 | Sprint 2026-Q1-1 | Dashboard & Reporting Engine | tech-debt, api | 13 | CI/CD | v2.0.0 | 7.4 | 30.8
SPARK-64 | Task: Document data pipeline architecture | Bug | Done | Medium | Frank Johnson | Bob Martinez | 2025-10-16 | 2025-10-30 | 2025-10-30 |  | Sprint 2025-Q4-2 | Data Pipeline Modernization | performance | 13 | Mobile iOS | v2.1.0 | 37 | 34
SPARK-65 | [User] Additional work item #65 | Task | In Review | Low | David Kim | Grace Liu | 2025-11-01 | 2025-11-18 |  | 2025-11-12 | Sprint 2025-Q4-3 | User Authentication & SSO | performance | 1 | Mobile iOS |  |  | 2.7
SPARK-66 | Spike: Evaluate WebSocket for real-time data push | Bug | To Do | Low | Alice Chen | Bob Martinez | 2026-01-22 | 2026-01-28 |  | 2026-02-05 | Sprint 2026-Q1-2 | Dashboard & Reporting Engine | tech-debt | 3 | Mobile iOS
SPARK-67 | [User] Additional work item #67 | Story | Done | Highest | Bob Martinez | Eva Petrov | 2025-10-03 | 2025-10-19 | 2025-10-19 | 2025-10-17 | Sprint 2025-Q4-1 | User Authentication & SSO | analytics | 3 | API Gateway | v2.0.0 | 11.7 | 9.4
SPARK-68 | [Mobile] Additional work item #68 | Bug | To Do | Medium | Alice Chen | Alice Chen | 2026-01-17 | 2026-01-26 |  |  | Sprint 2026-Q1-2 | Mobile App v2 Redesign | performance, tech-debt | 2 | API Gateway | v3.0.0-beta |  | 7
SPARK-69 | [Dashboard] Additional work item #69 | Bug | Done | Medium | Grace Liu | Alice Chen | 2026-01-20 | 2026-02-04 | 2026-02-04 |  | Sprint 2026-Q1-2 | Dashboard & Reporting Engine | ux, documentation, database | 3 | Shared Libs | v3.0.0-beta | 6 | 6.3
SPARK-70 | [Mobile] Additional work item #70 | Story | Done | High | Grace Liu | PM - Sarah Wilson | 2025-10-25 | 2025-11-04 | 2025-11-04 |  | Sprint 2025-Q4-3 | Mobile App v2 Redesign | analytics, api | 2 | API Gateway | v2.0.0 | 7.1 | 8.2
SPARK-71 | Task: Set up staging environment for pipeline testing | Task | Done | Low | David Kim | Bob Martinez | 2025-10-26 | 2025-11-02 | 2025-11-02 | 2025-11-10 | Sprint 2025-Q4-3 | Data Pipeline Modernization | analytics | 1 | CI/CD | v3.0.0-beta | 6.6 | 4.7
SPARK-72 | [Data] Additional work item #72 | Story | To Do | Medium | Eva Petrov | Eva Petrov | 2025-10-24 | 2025-11-04 |  | 2025-11-12 | Sprint 2025-Q4-3 | Data Pipeline Modernization | backend, database | 5 | Mobile Android |  |  | 27.3
SPARK-73 | [User] Additional work item #73 | Bug | In Review | Medium | Alice Chen | Hassan Ali | 2026-01-17 | 2026-01-27 |  | 2026-02-06 | Sprint 2026-Q1-2 | User Authentication & SSO | infra | 2 | API Gateway
SPARK-74 | [User] Additional work item #74 | Bug | To Do | Low | Hassan Ali | PM - Sarah Wilson | 2026-01-22 | 2026-01-27 |  | 2026-02-02 | Sprint 2026-Q1-2 | User Authentication & SSO | analytics, tech-debt | 5 | Web App
SPARK-75 | [User] Additional work item #75 | Story | Done | Medium | Carol Okonkwo | Frank Johnson | 2025-10-25 | 2025-11-16 | 2025-11-16 | 2025-11-13 | Sprint 2025-Q4-3 | User Authentication & SSO | mobile, accessibility, ux | 3 | Auth Service | v2.0.0 | 9.7 | 9.7
SPARK-76 | [Data] Additional work item #76 | Bug | Done | Low | Bob Martinez | Grace Liu | 2025-10-18 | 2025-10-19 | 2025-10-19 | 2025-10-27 | Sprint 2025-Q4-2 | Data Pipeline Modernization | analytics, infra | 2 | Data Service | v2.1.0 | 4.9 | 5.2
SPARK-77 | [User] Additional work item #77 | Task | Done | Low | Alice Chen | Frank Johnson | 2026-01-16 | 2026-01-29 | 2026-01-29 | 2026-01-31 | Sprint 2026-Q1-2 | User Authentication & SSO | infra, backend, ux | 2 | Mobile Android |  | 6.2 | 5.9
SPARK-78 | [Data] Additional work item #78 | Story | In Progress | Lowest | Hassan Ali | David Kim | 2026-01-05 | 2026-01-23 |  |  | Sprint 2026-Q1-1 | Data Pipeline Modernization | analytics, ux | 5 | Shared Libs |  | 13.7 | 26.3
SPARK-79 | [Dashboard] Additional work item #79 | Story | Done | Medium | Bob Martinez | PM - Sarah Wilson | 2025-10-25 | 2025-10-28 | 2025-10-28 |  | Sprint 2025-Q4-3 | Dashboard & Reporting Engine | database, testing | 3 | Auth Service |  | 10.1 | 7.1
SPARK-80 | [Mobile] Additional work item #80 | Spike | In Review | Medium | Frank Johnson | David Kim | 2025-10-30 | 2025-11-01 |  | 2025-11-08 | Sprint 2025-Q4-3 | Mobile App v2 Redesign | auth | 3 | Mobile Android |  |  | 9.4
SPARK-81 | [Mobile] Additional work item #81 | Task | Done | Medium | Bob Martinez | Alice Chen | 2025-10-14 | 2025-10-19 | 2025-10-19 | 2025-11-02 | Sprint 2025-Q4-2 | Mobile App v2 Redesign | analytics | 5 | Mobile iOS | v2.0.0 | 11.3 | 11
SPARK-82 | [Mobile] Additional work item #82 | Story | Done | Medium | Alice Chen | PM - Sarah Wilson | 2025-09-29 | 2025-10-04 | 2025-10-04 | 2025-10-11 | Sprint 2025-Q4-1 | Mobile App v2 Redesign | security, documentation | 8 | Shared Libs | v2.0.0 | 32.4 | 32.8
SPARK-83 | [User] Additional work item #83 | Sub-task | To Do | Medium | Frank Johnson | Eva Petrov | 2025-12-31 | 2026-01-11 |  |  | Sprint 2026-Q1-1 | User Authentication & SSO | mobile | 1 | API Gateway
SPARK-84 | [Data] Additional work item #84 | Story | Done | Low | Carol Okonkwo | Hassan Ali | 2025-10-17 | 2025-10-22 | 2025-10-22 | 2025-11-01 | Sprint 2025-Q4-2 | Data Pipeline Modernization | security, backend | 1 | Data Service |  | 3.1 | 3.3
SPARK-85 | [Mobile] Additional work item #85 | Story | To Do | Medium | Eva Petrov | Frank Johnson | 2026-01-14 | 2026-02-03 |  | 2026-01-30 | Sprint 2026-Q1-2 | Mobile App v2 Redesign | database, ux | 3 | CI/CD |  |  | 17.7
SPARK-86 | [Mobile] Additional work item #86 | Story | Done | Medium | Bob Martinez | Grace Liu | 2026-01-01 | 2026-01-21 | 2026-01-21 |  | Sprint 2026-Q1-1 | Mobile App v2 Redesign | performance, tech-debt, frontend | 2 | API Gateway | v2.2.0 | 7.6 | 6.5
SPARK-87 | [Mobile] Additional work item #87 | Bug | In Review | Highest | Frank Johnson | PM - James Taylor | 2025-10-16 | 2025-10-24 |  | 2025-10-25 | Sprint 2025-Q4-2 | Mobile App v2 Redesign | accessibility, ux, tech-debt | 1 | Auth Service |  |  | 4.4
SPARK-88 | [Mobile] Additional work item #88 | Story | In Progress | Medium | Frank Johnson | Grace Liu | 2025-09-26 | 2025-10-15 |  | 2025-10-18 | Sprint 2025-Q4-1 | Mobile App v2 Redesign | infra, analytics | 3 | API Gateway | v2.2.0 | 5 | 10.8
SPARK-89 | [Dashboard] Additional work item #89 | Story | In Progress | Medium | Bob Martinez | Eva Petrov | 2025-09-30 | 2025-10-14 |  | 2025-10-15 | Sprint 2025-Q4-1 | Dashboard & Reporting Engine | security, frontend | 13 | Auth Service |  | 27.7 | 49.5
SPARK-90 | [Mobile] Additional work item #90 | Task | Blocked | Lowest |  | Bob Martinez | 2025-10-04 | 2025-10-21 |  | 2025-10-15 | Sprint 2025-Q4-1 | Mobile App v2 Redesign | mobile, database, accessibility | 2 | Auth Service
SPARK-91 | [Dashboard] Additional work item #91 | Story | Done | Medium | Frank Johnson | Hassan Ali | 2025-10-18 | 2025-10-28 | 2025-10-28 |  | Sprint 2025-Q4-2 | Dashboard & Reporting Engine | ux, mobile | 1 | CI/CD | v3.0.0-beta | 4 | 5.3
SPARK-92 | [Data] Additional work item #92 | Story | Done | Medium | Carol Okonkwo | Carol Okonkwo | 2025-10-02 | 2025-10-04 | 2025-10-04 |  | Sprint 2025-Q4-1 | Data Pipeline Modernization | performance | 8 | Auth Service | v2.1.0 | 39.3 | 27.1
SPARK-93 | [Data] Additional work item #93 | Story | Done | Medium | Carol Okonkwo | Eva Petrov | 2025-10-04 | 2025-10-13 | 2025-10-13 | 2025-10-13 | Sprint 2025-Q4-1 | Data Pipeline Modernization | documentation, mobile, database | 2 | Mobile Android |  | 11.6 | 8.5
SPARK-94 | [User] Additional work item #94 | Story | Done | Medium | David Kim | PM - James Taylor | 2025-10-02 | 2025-10-03 | 2025-10-03 | 2025-10-19 | Sprint 2025-Q4-1 | User Authentication & SSO | performance, infra, security | 3 | Shared Libs | v2.0.0 | 11.8 | 14.3
SPARK-95 | [Mobile] Additional work item #95 | Story | In Progress | High | Frank Johnson | Frank Johnson | 2026-01-06 | 2026-01-10 |  |  | Sprint 2026-Q1-1 | Mobile App v2 Redesign | frontend, tech-debt, security | 8 | CI/CD | v3.0.0-beta | 5.7 | 23.9
SPARK-96 | [Data] Additional work item #96 | Sub-task | In Review | Lowest | Carol Okonkwo | Frank Johnson | 2026-01-05 | 2026-01-11 |  |  | Sprint 2026-Q1-1 | Data Pipeline Modernization | infra, database, performance | 1 | CI/CD | v3.0.0-beta
SPARK-97 | [Dashboard] Additional work item #97 | Bug | To Do | Medium | Hassan Ali | Eva Petrov | 2025-10-18 | 2025-10-18 |  |  | Sprint 2025-Q4-2 | Dashboard & Reporting Engine | database | 5 | Mobile iOS
SPARK-98 | [Data] Additional work item #98 | Story | Done | High | Eva Petrov | Bob Martinez | 2025-10-02 | 2025-10-17 | 2025-10-17 |  | Sprint 2025-Q4-1 | Data Pipeline Modernization | accessibility, documentation, frontend | 3 | Auth Service |  | 14.3 | 10.7
SPARK-99 | [Data] Additional work item #99 | Spike | Done | High | Grace Liu | PM - Sarah Wilson | 2026-01-14 | 2026-01-16 | 2026-01-16 | 2026-02-03 | Sprint 2026-Q1-2 | Data Pipeline Modernization | infra, api, documentation | 5 | Auth Service | v2.2.0 | 19.8 | 13.3
SPARK-100 | [Data] Additional work item #100 | Story | Done | Medium | Eva Petrov | Hassan Ali | 2026-01-14 | 2026-01-25 | 2026-01-25 | 2026-02-04 | Sprint 2026-Q1-2 | Data Pipeline Modernization | analytics, mobile | 8 | Web App | v2.2.0 | 62.3 | 46.9